# MIRAGE-SHIELD Development Roadmap

Oct 19, 2026 · @prajit

## Mission and deadline

We ship MIRAGE-SHIELD, a living-room defence against "digital arrest" and courier-extortion scams, by Oct 24, 00:30 IST (Oct 23, 12:00 PM PDT). Confirm this on the Devpost page today; plan to submit by Oct 23, 18:00 IST to keep a 6-hour buffer.

Core claim: Scammers win by lying about the physical world ("officers are outside your door", "a parcel in your name was seized") while keeping the victim isolated on a video call. MIRAGE-SHIELD catches the lie with three signals and breaks the isolation on the biggest screen in the house.

- Ring as the evidence oracle. Ring event history, live status and snapshots prove whether anyone or any parcel actually came to the door.

- Deepfake and coercion detection. Our deepfake model checks the scam video call; a classifier flags coercion scripts in the transcript.

- Fire TV intervention. A Vega OS app takes over the TV with the evidence, the law, the 1930 helpline and a family alert, while payments stay locked.

Entries: Ring primary track (fallback: Fire TV if the gallery looks thinner there on Oct 23), AWS Builder mini challenge, Open Source mini challenge.

Working mode: one team, one roadmap. Everyone works the same phase together; nobody starts the next phase until the current gate passes.

## System architecture

MIRAGE-SHIELD architecture · 2 inputs, 1 agent, 4 outputs

The agent intervenes only when the call looks manipulated or coercive and Ring contradicts what the caller claims about the door.

Stack: Python (FastAPI) for the Ring service and detector; Strands Agents SDK on Bedrock, deployed to AgentCore Runtime or Lambda; AWS KMS and DynamoDB for signed incident records; Vega OS React Native app (fallback: Fire OS) for the TV; a small web console for the phone and family views; ring-api-helloworld, ringpartner and ring-sandbox for Ring access and testing.

## Compliance checklist

Every item below is a disqualification or scoring risk, so we design against it from the first commit.

| Rule | What it means for us |
| --- | --- |
| Ring tech must be called in code | Real calls to api.amazonvision.com (devices, event history, snapshots, webhooks, chime playback) in the main code path, not only in the README |
| Demo via simulator or device | Ring Developer Playground token or emulator is fine; show it working on screen |
| Video under 3 minutes, public, English | YouTube or Vimeo; best material in the first 30 seconds |
| No third-party footage or music | Film our own scam-call clips; use royalty-free or no music |
| Repo has all source and run instructions | One-command setup in README; .env.example, no secrets committed |
| Public repo with OSI license, or private and shared | Default: public with MIT license on submission day (avoids expiring collaborator invites) |
| Product feedback for every tool used | Ring API, Vega SDK, Bedrock/AgentCore, Kiro: what worked, what didn't, onboarding, would we reuse |
| AWS Builder fields | Document each AWS service and how it is used |
| Open Source fields | Contribution URL, repo URL, GitHub username, what/how/why |
| Friction log (optional, up to 10% bonus) | Task, steps, expected vs actual, severity, workaround, suggestion; target 6 to 8 entries |
| Honest scoping | State plainly: simulator footage, test-mode payments, staged scam call |

Rule for the whole build: the moment anyone hits friction with a tool, they add a friction-log row in the shared sheet before fixing it.

## Day 1 (Oct 19, evening to Oct 20, morning): foundations

Goal: every external dependency answers a hello-world call before anyone writes product code.

Block 1 — Decisions and repo (2 hours)

- ☐ Confirm the deadline and rules on the Devpost page; register the team

- ☐ Answer two blocking questions: does anyone own a Ring doorbell? Is anyone on macOS or Ubuntu for the Vega tools?

- ☐ Create the monorepo: /ring-service, /detector, /agent, /firetv-app, /web-console, /docs

- ☐ If using Kiro, open the repo in Kiro and commit the /.kiro folder from commit 1

- ☐ Add MIT license, README skeleton, .env.example, .gitignore

- ☐ Create the friction-log sheet and the product-feedback notes file

Block 2 — Ring access (3 hours)

- ☐ Clone AmazonAppDev/ring-api-helloworld and run it

- ☐ Get a Developer Playground token (30-minute expiry) and call GET /v1/devices

- ☐ Call event history, a snapshot, and device configurations; save the raw responses as fixtures

- ☐ Check whether a chime device exists in the playground and list its audio_ref slots

- ☐ Install the ring-sandbox emulator so work never blocks on token expiry

Block 3 — Fire TV and AWS access (3 hours)

- ☐ Install Vega Developer Tools and boot the Vega Virtual Device; run vega-video-sample

- ☐ If Vega tools fail on our machines, fall back to a Fire OS app (React Native or Kotlin) on the Android TV emulator

- ☐ Enable Bedrock model access in our AWS account; make one test call from Python

- ☐ Install the Strands Agents SDK and run its hello-world agent

Block 4 — Interface contracts (1 hour)

- ☐ Write the JSON schema for the three messages the system passes: DoorEvidence, CallRisk, Verdict

- ☐ Commit sample JSON for each so every component can be built against fakes

Gate to Day 2: a Ring device list, a Vega app on screen, a Bedrock reply, and the three schemas are all in the repo.

## Day 2 (Oct 20): core pipelines

Goal: each of the four pipelines works on its own against fake inputs from the Day 1 schemas.

Pipeline A — Ring evidence service

- ☐ Webhook endpoint with HMAC-SHA256 verification; respond 200 within 5 seconds and process asynchronously

- ☐ get_door_evidence(window) tool: queries event history for human, vehicle, package and ding events in the last N hours

- ☐ Fetch the latest snapshot for the window and store its hash

- ☐ Return a DoorEvidence object: "0 people, 0 parcels in 6 hours" plus snapshot link

- ☐ Chime alert: play one pre-loaded audio_ref when a scam is confirmed (skip if no chime in playground)

Pipeline B — Scam-call detector

- ☐ Record our own staged scam calls (fake "officer", fake police backdrop) and genuine calls as test clips

- ☐ Adapt our existing deepfake model to score video frames from a call clip; output a 0–1 manipulation score

- ☐ Speech-to-text on the call audio (Amazon Transcribe or Whisper)

- ☐ Coercion-script classifier on the transcript: flags isolation demands, fake warrants, seized-parcel claims, payment demands

- ☐ Extract physical-world claims ("officers at your door", "parcel seized") as structured items for the agent to check

- ☐ Return a CallRisk object

Pipeline C — Agent brain

- ☐ Strands agent with tools: get_door_evidence, score_call, lock_payments, notify_family, trigger_tv_alert

- ☐ Decision logic: deepfake score + coercion flags + Ring contradicting a claim → Verdict (safe / warn / intervene)

- ☐ Payment lock: a test-mode transfer stays blocked while an intervention is active; family co-sign releases it

- ☐ Sign each verdict with AWS KMS and store it in DynamoDB as an incident record

- ☐ Deploy to AgentCore Runtime if time allows; otherwise Lambda, and note it

Pipeline D — Fire TV app

- ☐ Home screen and a full-screen intervention screen with D-pad focus

- ☐ Intervention screen shows: Ring snapshot and "no one at your door" evidence, the deepfake score, the line "police never arrest over video call", 1930 helpline, family notified

- ☐ Poll or subscribe to the backend for new verdicts

Gate to Day 3: each pipeline returns correct output for one scam clip and one genuine clip, using fakes for its neighbours.

## Day 3 (Oct 21): end-to-end integration

Goal: one staged scam call flows through the whole system and ends on the Fire TV screen with no manual steps.

Morning — wire the loop

- ☐ Replace every fake with the real component: call clip → detector → agent → Ring evidence → verdict → Fire TV + chime + family alert

- ☐ Web console (the "victim's phone" view): plays the scam call, shows live risk score, tries a payment that gets blocked

- ☐ Family view: receives the alert and can co-sign to release a payment

- ☐ Measure time from the scam claim being spoken to the TV takeover; target under 10 seconds

Afternoon — the three demo scenarios

- ☐ Scenario 1, scam caught: fake officer claims a seized parcel and officers outside; Ring shows nobody → intervene

- ☐ Scenario 2, genuine call: a real relative calls, no coercion, no deepfake → stays quiet (proves low false alarms)

- ☐ Scenario 3, real courier: Ring shows a genuine package event; the agent confirms it and does not raise a false alarm

- ☐ Run each scenario 5 times; log failures and fix the top two

Evening — open source and hardening

- ☐ Extract the Ring evidence tool into a standalone MIT-licensed package (e.g. ring-evidence-mcp) or open a PR on ring-sandbox adding the scam-scenario scripts

- ☐ Write its README: what it does, how it works, why it matters

- ☐ Handle the 30-minute token expiry, webhook retries and empty event history gracefully

- ☐ Optional, only with a physical Ring doorbell: passive screen-replay check on the door snapshot

Gate to Day 4: all three scenarios pass 5 times in a row on a clean clone using the README steps.

## Day 4 (Oct 22 to Oct 23): freeze, film, submit

Goal: a submitted entry by Oct 23, 18:00 IST, six and a half hours before the hard deadline.

Oct 22, morning — polish

- ☐ Fix only demo-path bugs; no new features after 12:00 IST

- ☐ Make the Fire TV intervention screen look finished: large type, high contrast, clear evidence panel

- ☐ Clean-clone test: someone who did not write the code follows the README on a fresh machine

Oct 22, afternoon — feature freeze at 16:00 IST, then film

- ☐ Record each demo scenario screen-by-screen at 1080p; record a backup take of everything

- ☐ Record the voice-over separately for clean audio

- ☐ Edit to under 2:55; check no third-party music or footage is in it

- ☐ Upload to YouTube as public; watch it once on a phone

Oct 22, evening — write-ups

- ☐ Devpost description: problem, how it works, architecture image, what's real vs simulated

- ☐ Product feedback for Ring API, Vega SDK, Bedrock/AgentCore/Strands, Kiro

- ☐ AWS Builder section: each service and its role

- ☐ Open Source section: contribution URL, repo URL, GitHub username, description

- ☐ Friction log: clean up to 6 to 8 strong entries

- ☐ Optional feature requests with urgency labels

Oct 23 — submit

- ☐ Make the repo public with the MIT license (or private + add the six reviewers today)

- ☐ Final read of every submission field by two people

- ☐ Submit by 18:00 IST; screenshot the confirmation

- ☐ After submitting: check the Devpost gallery and decide Ring vs Fire TV primary track only if editing is still allowed

## Demo video script (2:55)

The scam-caught moment lands inside the first 60 seconds, because judges may stop watching at any point.

| Time | On screen | Voice-over (gist) |
| --- | --- | --- |
| 0:00–0:15 | Black screen, one verified statistic, then a phone ringing | Digital arrest scams are draining Indian seniors; the scam starts with a lie about the physical world |
| 0:15–0:55 | Split screen: fake "officer" video call on the phone, the living-room TV, the Ring feed | The officer claims a seized parcel and police at the door; the deepfake score climbs |
| 0:55–1:25 | Agent checks Ring: zero people, zero parcels; TV takes over with the evidence; chime sounds; payment attempt blocked | Ring proves the claim is false; the TV breaks the isolation the scammer depends on |
| 1:25–1:45 | Family phone gets the alert; co-sign view | Family is pulled back in; money stays locked until they co-sign |
| 1:45–2:10 | Scenario 2 and 3 quickly: genuine call stays quiet; real courier is confirmed | It doesn't cry wolf: real people and real parcels pass |
| 2:10–2:35 | Architecture image; Ring API calls highlighted; signed incident record | How it works: Ring evidence, deepfake model, Bedrock agent, Fire TV app |
| 2:35–2:55 | Team, open-source package, one-line close | Scammers lie about the front door. Ring tells the truth. |

## Risks, fallbacks and cut order

The Ring evidence check and the Fire TV takeover are the product; everything else can be cut.

| Risk | Fallback |
| --- | --- |
| Vega tools won't install on our machines | Fire OS app on the Android TV emulator; same screens |
| Playground token expires mid-demo | Record against ring-sandbox fixtures captured from the real API; say so in the write-up |
| No chime device in the playground | Drop the chime; the TV takeover carries the alert |
| Deepfake model weak on call video | Lean on coercion-script detection plus the Ring contradiction; show the deepfake score as one signal |
| Bedrock model access delayed | Strands with any already-enabled model; keep AWS for KMS, DynamoDB and Lambda |
| AgentCore deployment fails | Run the Strands agent on Lambda and note it in the AWS section |
| Integration slips past Day 3 | Hard-wire the scenario order for the demo; keep the Ring calls real |

Cut order if we fall behind:

- Chime alert

- Family co-sign screen (keep the notification)

- AgentCore (use Lambda)

- Scenario 3, real courier

- Deepfake video score (keep transcript coercion detection)

Never cut: real Ring API calls, the Fire TV intervention screen, Scenario 1.

## Facts to verify and final checklist

Nothing from the Gemini report goes into the pitch until it is checked against a primary source.

Verify before use

- ☐ Digital arrest loss figures: use MHA or I4C sources directly; the 2025 figure in the report may be total cyber fraud, not digital arrest alone

- ☐ Competitor projects named in the report (ATLAS Steward, VoiceGuard MCP, Hold On): confirm in the Devpost gallery

- ☐ AgentCore, Strands and model version names: take them from the docs at install time

- ☐ Vega Developer Tools OS support

- ☐ Whether the Ring playground exposes a chime and which event types it simulates

Already verified in Ring's official docs

- Live video over WHEP is receive-only video, with no audio

- Chime playback plays a pre-set audio_ref slot; it cannot speak arbitrary text

- All Ring media carries a visible watermark

- The simulator offers package, vehicle and motion live-view events

Final submission checklist

- ☐ Text description

- ☐ Repo link: public with MIT license, or private with all six reviewers added

- ☐ Demo video link, public, under 3 minutes, English

- ☐ Product feedback for every tool

- ☐ Track and mini challenges selected

- ☐ AWS Builder fields

- ☐ Open Source fields

- ☐ Friction log entries

- ☐ Statement of what is real, simulated and test-mode

Sources: Ring Partner API documentation · Ring live video streaming · Ring release notes · ring-api-helloworld · ringpartner Python SDK · Devpost hackathon page